## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | PROJ324 - SCV-E
Enter Company Name in cell B2. | Student 10588101
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Zil-E-Hasnain Shah | Project Start: |  | 2020-11-20
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30 | [6 empty] | 2020-12-07 | [6 empty] | 2020-12-14 | [6 empty] | 2020-12-21 | [6 empty] | 2020-12-28 | [6 empty] | 2021-01-04 | [6 empty] | 2021-01-11 | [6 empty] | 2021-01-18 | [6 empty] | 2021-01-25 | [6 empty] | 2021-02-01 | [6 empty] | 2021-02-08 | [6 empty] | 2021-02-15 | [6 empty] | 2021-02-22 | [6 empty] | 2021-03-01 | [6 empty] | 2021-03-08 | [6 empty] | 2021-03-15 | [6 empty] | 2021-03-22 | [6 empty] | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12 | [6 empty] | 2021-04-19 | [6 empty] | 2021-04-26 | [6 empty] | 2021-05-03 | [6 empty] | 2021-05-10 | [6 empty] | 2021-05-17 | [6 empty] | 2021-05-24 | [6 empty] | 2021-05-31 | [6 empty] | 2021-06-07 | [6 empty] | 2021-06-14 | [6 empty] | 2021-06-21 | [6 empty] | 2021-06-28 | [6 empty] | 2021-07-05 | [6 empty] | 2021-07-12 | [6 empty] | 2021-07-19 | [6 empty] | 2021-07-26 | [6 empty] | 2021-08-02 | [6 empty] | 2021-08-09 | [6 empty] | 2021-08-16 | [6 empty] | 2021-08-23 | [6 empty] | 2021-08-30 | [6 empty] | 2021-09-06 | [6 empty] | 2021-09-13 | [6 empty] | 2021-09-20 | [6 empty] | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-11-16 to 2022-01-09
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2020-11-16 to 2022-01-09
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Research Phase
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Construction vehicle |  | 100% | 2020-11-20 | 2020-11-20 | 1
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Batteries |  | 100% | 2020-12-01 | 2021-04-05 | 126
| Crane |  | 100% | 2021-08-08 | 2021-11-20 | 105
| Controller market |  | 100% | 2021-02-16 | 2021-03-21 | 34
| Componets research |  | 100% | 2020-11-20 | 2021-01-01 | 43
| Platform software |  | 100% | 2020-12-02 | 2020-12-04 | 3
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Design Phase
| Initial CAD model of SCV |  | 100% | 2020-12-03 | 2021-01-12 | 41
| Re-itereation of SCV |  | 100% | 2021-04-03 | 2021-07-25 | 114
| PCB Circuit for SCV |  | 100% | 2021-10-01 | 2021-11-01 | 32
| PCB Circuit for Controller |  | 100% | 2020-11-20 | 2021-02-16 | 89
| CAD model of controller | 80% | 100% | 2021-02-20 | 2021-06-06 | 107
| CAD model of base station |  | 100% | 2020-12-12 | 2021-03-25 | 104
Sample phase title block | Manufacturing Phase
| 3D printing |  | 100% | 2020-12-05 | 2021-12-07 | 368
| Assembling Controller |  | 100% | 2021-05-05 | 2021-08-08 | 96
| Assembling base station | 80% | 100% | 2021-05-10 | 2021-05-15 | 6
| Assembling SCV |  | 100% | 2021-05-16 | 2021-12-06 | 205
| Programming Base station |  | 100% | 2021-09-01 | 2021-09-05 | 5
| Programming SCV |  | 100% | 2021-07-06 | 2021-12-06 | 154
| Assembling Makeshift Controller |  | 100% | 2021-11-26 | 2021-11-30 | 5
| Programming Controller |  | 100% | 2021-12-01 | 2021-12-06 | 6
Sample phase title block | Testing
| Controller |  | 100% | 2021-12-02 | 2021-12-06 | 5
| SCV |  | 100% | 2021-12-02 | 2021-12-06 | 5
Deliverable
| Main components delivered |  | 100% | 2021-01-01 | 2021-04-06 | 96
| Second batch components delivered |  | 100% | 2021-05-15 | 2021-06-01 | 18
| Third batch components delivered |  | 100% | 2021-10-02 | 2021-11-02 | 32
Disruption during project
| Covid Self isolation #1 |  | 100% | 2020-12-26 | 2021-01-14 | 20
| Covid Self isolation #2 |  | 100% | 2021-08-14 | 2021-08-30 | 17
| Family Death Covid |  | 100% | 2021-05-06 | 2021-05-06 | 1
| Family Death Covid |  | 100% | 2021-08-07 | 2021-08-07 | 1
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one

## BUDGET SUMMARY
Itemized Expenses
PROJ324 | PROJECT BUDGET
PROJECT INFORMATION
Project Name | SCV-E
Project Description | Dump Truck Type Buggy with Crane lifter and Live Video Feedback, Charging base and Custom Controller included
Contractor | -
Student ID | 10588101
Student Name | Hasnain Shah
OneNote Link | PROJECT SHOWCASE
SuperVisor | Shakil Awan Ahmed
FullFilled Date | 9th december 2021
FINANCIAL STATUS
Account | Amount
Planned Amount | 500
Sponsored Amount | 250
Additional Amount put in | 1500
Loaned Amount | 500
Total Allotted Funds | 2750
Funds Used To Date | 2740.908
Project Cost | 667.855
Funds Remaining | 9.092
ENTER EXPENSES

## ITEMIZED EXPENSES
Budget Summary
LIST | OF EXPENSES
PROJECT FUNDS ALLOTTED |  | FUNDS USED TO DATE |  |  | PROJECT COST |  |  | FUNDS REMAINING
2750 |  | 2740.908 |  |  | 667.855 |  |  | 9.092
Item | Supplier | Category | Type | QTY | Purchase Cost | Price Per QTY | Used QTY | Used Cost
TS5828s 200MW 5.8G 40ch FPV Camera | AliExpress | Materials | Buggy | 1 | 17.78 | 17.78 | 1 | 17.78
50 Pairs Metal Battery Spring plate | AliExpress | Materials | Buggy | 50 | 3.33 | 0.0666 | 0 | 0
GT-24 Wireless module 2.4G NRF24L01 | AliExpress | Materials | Buggy | 1 | 2.24 | 2.24 |  | 0
Mechanic UV Solder Mask INK PCB | AliExpress | Equipment | All | 1 | 3.63 | 3.63 | 0.5 | 1.815
N35 Neodymium magnets | AliExpress | Materials | Base Station | 50 | 4.25 | 0.085 | 4 | 0.34
N50 Neodymium magnets | AliExpress | Materials | Buggy | 20 | 8 | 0.4 | 8 | 3.2
50N Solenoid Electromagnet 5V + IP65 | AliExpress | Materials | Buggy | 1 | 2.68 | 2.68 | 1 | 2.68
25N Solenoid Electromagnet 5V + IP65 | AliExpress | Materials | None | 1 | 1.97 | 1.97 | 0 | 0
Crocodile Clips | AliExpress | Equipment | All | 10 | 1.27 | 0.127 | 0 | 0
Mechanic Paste Flux 10CC SMD PCB | AliExpress | Equipment | All | 2 | 3.75 | 1.875 | 0.5 | 0.9375
Alligator test clip to Jumper cable 30cm | AliExpress | Equipment | All | 5 | 2.16 | 0.432 | 5 | 2.16
Toggle Switch 125V 6A ON-ON 2POS+3PIN | AliExpress | Materials | Controller | 5 | 2.55 | 0.51 |  | 0
Potentiometer 10K ohm | AliExpress | Materials | Controller | 5 | 1.91 | 0.382 |  | 0
100x100 mm Thermal Pad heatsink | AliExpress | Materials | Buggy | 2 | 6.71 | 3.355 | 2 | 6.71
4S 40A BMS LIPO with balancer | AliExpress | Materials | Buggy | 1 | 3.33 | 3.33 | 1 | 3.33
SMD LED 5730 kit | AliExpress | Materials | None | 100 | 2.1 | 0.021 |  | 0
BGA Reballing 1 Bottle 0.76 mm | AliExpress | Materials | None | 1 | 1.37 | 1.37 | 0 | 0
GT-24 Wireless module 2.4G NRF24L01 | AliExpress | Materials | Controller | 1 | 2.24 | 2.24 | 1 | 2.24
Type C PD3.0 Trigger Spoof | AliExpress | Materials | None | 1 | 5.74 | 5.74 | 1 | 5.74
15W Qi Wireless charger | AliExpress | Materials | Base Station | 1 | 8.28 | 8.28 | 1 | 8.28
Battery Insulator gasket 1000x120 mm | AliExpress | Materials | B+C | 1 | 1.65 | 1.65 |  | 0
4PCS 110x48 mm 1/10 Wheel set | AliExpress | Materials | Buggy | 4 | 14.9 | 3.725 | 4 | 14.9
Push button Vertical Set 4 pin | AliExpress | Materials | Controller | 100 | 2.56 | 0.0256 | 10 | 0.256
4x360 Servo 35KG | AliExpress | Materials | Buggy | 4 | 30.59 | 7.6475 | 5 | 38.2375
ESD Heat soldering Mat | AliExpress | Materials | All | 1 | 8.29 | 8.29 |  | 0
DC Motor 5-200 rpm Hall Encoder | AliExpress | Materials | Buggy | 4 | 23.21 | 5.8025 | 4 | 23.21
Micro Switches assorted 10 type ea | AliExpress | Materials | Controller | 100 | 3.55 | 0.0355 |  | 0
JST-XH JST + Dupont connector Kit + crimping tool | AliExpress | Materials | All | 1080 | 15.94 | 0.014759 | 5 | 0.073796
5000 mAh Li-po Batteries 3.7V | AliExpress | Materials | Controller | 4 | 11.73 | 2.9325 | 0 | 0
10000 mAh Li-po Batteries 3.7V | AliExpress | Materials | None | 2 | 9.6 | 4.8 | 0 | 0
Panasonic 21700 4800mAh +PCB 40A | AliExpress | Loss (Scammed) | Buggy | 40 | 80.31 | 2.0078 | 0 | 0
Carbon Fiber Hydro dip | AliExpress | Materials | Controller | 1 | 5.92 | 5.92 |  | 0
Joystick 3D analog PS2 | AliExpress | Materials | Controller | 4 | 2.84 | 0.71 | 2 | 1.42
SMD LED 5050 RGB | AliExpress | Materials | None | 100 | 1.66 | 0.0166 |  | 0
Type C PD3.0 20V | AliExpress | Materials | Base Station | 1 | 1.445 | 1.445 | 1 | 1.445
Type C PD3.0 9V | AliExpress | Materials | Controller | 1 | 1.45 | 1.45 | 1 | 1.45
GY-521 MPU 6050 accelerometer | AliExpress | Materials | Controller | 1 | 6.75 | 6.75 | 1 | 6.75
E-DA TPU 1KG 1.75 mm Filament (Price per gram) | Amazon | Materials | All | 1000 | 20.98 | 0.02098 |  | 0
Gorilla Wood Glue 1L | Amazon | Equipment | Base Station | 1 | 9 | 9 |  | 0
Gorilla Super Glue 12g | Amazon | Equipment | All | 1 | 4.8 | 4.8 |  | 0
Gorilla Glue Contact Adhesive 75g | Amazon | Equipment | B+BS | 1 | 6.68 | 6.68 |  | 0
Dremel Moto scroll saw MS20 | Amazon | Equipment | All | 1 | 100.26 | 100.26 |  | 0
Banana Plug connector | Amazon | Materials | Buggy | 20 | 7.99 | 0.3995 | 10 | 3.995
Anycubic 3D printer PLA 1KG | Amazon | Materials | All | 1000 | 21.99 | 0.02199 |  | 0
LACO125AMZ-LA-CO Flux paste 125g | Amazon | Materials | All | 1 | 5.75 | 5.75 |  | 0
Hurricane 3 pc Pliers Set | Amazon | Equipment | All | 3 | 18.99 | 6.33 |  | 0
Copper Sheet 0.4x300x210 mm | Amazon | Materials | Buggy | 2 | 22 | 11 | 1.5 | 16.5
DC PSU LAB power bench 30V-10A max | Amazon | Equipment | All | 1 | 72.99 | 72.99 |  | 0
Resistor kit 1% 1/4 | Amazon | Materials | All | 1050 | 12.99 | 0.012371 | 20 | 0.24743
LED 5 mm | Amazon | Materials | B+C | 500 | 6.99 | 0.01398 |  | 0
PLA Filament 1 KG Generic Gray | Volt3D | Materials | All | 1000 | 10 | 0.01 | 1 | 0.01
PLA Filament 1 KG Evryone Black | Amazon | Materials | All | 1000 | 17.99 | 0.01799 | 1 | 0.01799
PLA Filament 1KG Evryone Glitter Black | Amazon | Materials | All | 1000 | 17.99 | 0.01799 |  | 0
Wifi Router Attenna IPEX4 | Amazon | Materials | Controller | 2 | 8.49 | 4.245 | 2 | 8.49
Arduino Nano 33 BLE Sense [ABX00031] | Amazon | Materials | Controller | 1 | 35.4 | 35.4 | 0 | 0
5.8G mini 72CH 200mW Eachine VTX03 | Banggood | Materials | Buggy | 1 | 8.96 | 8.96 |  | 0
Foxeer Razer 5MP HD Camera | Banggood | Materials | Buggy | 1 | 16.78 | 16.78 | 1 | 16.78
RX5805 5.8Ghz 48ch 480x320 5'' monitor | Banggood | Materials | Controller | 1 | 20.45 | 20.45 | 0 | 0
Simax3D Magnetic 3D printer Bed | Banggood | Replacement | All | 1 | 7.7 | 7.7 |  | 0
Hotend 24V 40W (creality) | Banggood | Replacement | All | 1 | 8.3 | 8.3 |  | 0
21700 Insulators | Fogstar Wholesale UK | Materials | Buggy | 100 | 4 | 0.04 | 1 | 0.04
21700 PVC Wraps - Black | Fogstar Wholesale UK | Materials | Buggy | 40 | 2.1 | 0.0525 | 1 | 0.0525
Samsung 21700 30T - 3.7V 30A | Fogstar Wholesale UK | Materials | Buggy | 40 | 115.6 | 2.89 | 22 | 63.58
Efest V8 - 21700 cell charger | Fogstar Wholesale UK | Equipment | All | 1 | 24.45 | 24.45 |  | 0
MDF 2440x1220 | B&Q UK | Materials | Base Station | 3 | 45 | 15 | 2.7 | 40.5
Controller Custom PCB [Y1-3442490B] | JCLB | Materials | Controller | 5 | 15.36 | 3.072 | 2 | 6.144
Micro JST PH2.0 2-pin plugs 10cm | Amazon | Materials | Controller | 20 | 5.99 | 0.2995 |  | 0
Choetecth USB C PD100W | Amazon | Equipment | Base Station | 1 | 49.99 | 49.99 | 1 | 49.99
Inductor 0.5W 1/2W | Amazon | Materials | All | 200 | 12.99 | 0.06495 | 2 | 0.1299
3 pin SPDT mini slide switch | Amazon | Materials | All | 55 | 7.49 | 0.13618 | 2 | 0.27236
Capacitor assortment kit | Amazon | Materials | All | 600 | 15.99 | 0.02665 | 2 | 0.0533
22AWG PVC 9M spool Blue (Price per cm) | Amazon | Materials | All | 900 | 2.333 | 0.0025922 | 30 | 0.077767
22AWG PVC 9M spool Black (Price per cm) | Amazon | Materials | All | 900 | 2.33 | 0.0025889 | 40 | 0.10356
22AWG PVC 9M spool Green (Price per cm) | Amazon | Materials | All | 900 | 2.33 | 0.0025889 | 50 | 0.12944
22AWG PVC 9M spool White (Price per cm) | Amazon | Materials | All | 900 | 2.33 | 0.0025889 | 10 | 0.025889
22AWG PVC 9M spool Yellow(Price per cm) | Amazon | Materials | All | 900 | 2.33 | 0.0025889 | 5 | 0.012944
22AWG PVC 9M spool Red (Price per cm) | Amazon | Materials | All | 900 | 2.33 | 0.0025889 | 40 | 0.10356
Arduino Mega 2560 Rev3 [A000067] | Amazon | Materials | Buggy | 1 | 35.7 | 35.7 | 0 | 0
YIXISI High Temperature Kapton Tape 3mm | Amazon | Materials | All | 330 | 1.7633 | 0.0053434 |  | 0
YIXISI High Temperature Kapton Tape 6mm | Amazon | Materials | All | 330 | 1.7633 | 0.0053434 |  | 0
YIXISI High Temperature Kapton Tape 8mm | Amazon | Materials | All | 330 | 1.7633 | 0.0053434 |  | 0
YIXISI High Temperature Kapton Tape 10mm | Amazon | Materials | All | 330 | 1.7633 | 0.0053434 |  | 0
YIXISI High Temperature Kapton Tape 12mm | Amazon | Materials | All | 330 | 1.7633 | 0.0053434 |  | 0
YIXISI High Temperature Kapton Tape 20mm | Amazon | Materials | All | 330 | 1.7633 | 0.0053434 | 30 | 0.1603
Arduino Mega R3 Elegoo | Amazon | Materials | Buggy | 1 | 11.89 | 11.89 | 1 | 11.89
PLA Filament ppx Black | Amazon | Materials | Controller | 1 | 18.38 | 18.38 | 1 | 18.38
First Aid Kit pack of 100 | Amazon | Safety | Human | 100 | 9.49 | 0.0949 | 12 | 1.1388
The One Paint Satin White + Dark Grey# | Amazon | Materials | Base Station | 1 | 37.98 | 37.98 | 0 | 0
Electric paint sprayer | Amazon | Equipment | All | 1 | 32.53 | 32.53 |  | 0
MDF Primer White | Amazon | Materials | Base Station | 1 | 9.9 | 9.9 |  | 0
Chisel Set tools | Amazon | Equipment | All | 1 | 27.99 | 27.99 | 0.2 | 5.598
Belt Sander Rent | Machinemarkt | Equipment | Base Station | 1 | 15.99 | 15.99 | 0 | 0
Geetech PETG Filament | Amazon | Materials | All | 1 | 23.99 | 23.99 | 1 | 23.99
Elegoo Mars Pro SLA printer | Amazon | Equipment | All | 1 | 130 | 130 |  | 0
Elegoo LCD UV 405nm ABS | Amazon | Materials | All | 1 | 38 | 38 |  | 0
Rubber Mallet fiberglas | Amazon | Equipment | All | 1 | 14.95 | 14.95 |  | 0
Primacreator Value UV FLEX resin | Amazon | Materials | All | 1 | 34.38 | 34.38 |  | 0
10 pin rainbow flat ribbon cable | Amazon | Materials | All | 1 | 7.19 | 7.19 |  | 0
Tronxy X5SA pro printer | Machinemarkt | Equipment | All | 1 | 339.98 | 339.98 | 0.1 | 33.998
Tecbears PLA Filament | Amazon | Materials | All | 5 | 64.95 | 12.99 | 4 | 51.96
Tecbears Petg Filament | Amazon | Materials | All | 1 | 11.99 | 11.99 |  | 0
Ball Bearing 8mm x22 mm x7 mm | Amazon | Materials | All | 8 | 6.49 | 0.81125 | 3 | 2.4337
HSS step drill bits | Amazon | Equipment | All | 3 | 12.34 | 4.1133 |  | 0
GT2 Pulley 8mm bore 6mm width | Amazon | Materials | All | 10 | 7.99 | 0.799 | 4 | 3.196
Deburing tool | Amazon | Equipment | All | 1 | 12.73 | 12.73 |  | 0
3D printer Glass platform holder | Amazon | Equipment | All | 100 | 7.99 | 0.0799 | 4 | 0.3196
Cable ties 100 | Amazon | Materials | All | 100 | 2.99 | 0.0299 | 25 | 0.7475
Tool star lock washers stainless steel | Amazon | Materials | All | 300 | 10.44 | 0.0348 | 3 | 0.1044
Dremel Workstation 220 | Amazon | Equipment | All | 1 | 29.24 | 29.24 |  | 0
PCA9685 16 channel | Amazon | Materials | Buggy | 2 | 7.59 | 3.795 | 1 | 3.795
360 pcs dupont wire | Amazon | Materials | All | 360 | 9.99 | 0.02775 | 100 | 2.775
L298N stepper motor driver | Amazon | Materials | Buggy | 5 | 9.99 | 1.998 | 3 | 5.994
Fuse wire | Amazon | Materials | Buggy | 3 | 2.9 | 0.96667 | 1 | 0.96667
Fuse holder | Amazon | Materials | Buggy | 1 | 2.99 | 2.99 | 1 | 2.99
Reed Magnetic switch | Amazon | Materials | Buggy | 10 | 7.99 | 0.799 |  | 0
150 mm linear actuator | Amazon | Materials | Buggy | 1 | 29.9 | 29.9 | 1 | 29.9
Dremel MS53 Saw blades | Amazon | Equipment | All | 5 | 6 | 1.2 | 3 | 3.6
Arduino BLE-NANO replica | Amazon | Materials | Controller | 1 | 22.6 | 22.6 | 1 | 22.6
Helping hands third hand soldering tool | Amazon | Equipment | All | 1 | 32.99 | 32.99 |  | 0
AZDelivery NRF24L01 | Amazon | Materials | All | 10 | 10.49 | 1.049 | 2 | 2.098
Metal Servo Arm 25T | Amazon | Materials | Buggy | 6 | 7.59 | 1.265 | 4 | 5.06
Hotend Nozzle | Amazon | Equipment | All | 10 | 6.99 | 0.699 | 3 | 2.097
Kywoo Tycoon Max 3D printer | Machinemarkt | Equipment | All | 1 | 447.99 | 447.99 | 0.05 | 22.3995
FPV monitor 5.8GHZ LCD | Amazon | Materials | Controller | 1 | 42.87 | 42.87 | 1 | 42.87
Carbon steel Ball Bearing | Amazon | Materials | All | 40 | 10.88 | 0.272 | 4 | 1.088
Rubbing Alcohol IPA | Amazon | Equipment | All | 2 | 30.99 | 15.495 | 1 | 15.495
Total |  |  |  |  | 2740.908 | 1983.635 |  | 667.855
BUDGET SUMMARY
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.